Module 2 — LiDAR Forest Inventory Analysis

Vegetation Monitoring with UAVs & LiDAR

Hard Deadline: 18 May 2026 ¦ Submit PDF + R Script to OneDrive or Fenix

| LEGEND | Hannah | Tiara | Person 3 | Person 4 | All / Shared |
| --- | --- | --- | --- | --- | --- |

Role Summaries

| Hannah LiDAR Processing & Methods Writing | Person 2 ABA Analysis & Introduction/Objectives | Person 3 ITD, Mapping & Results Writing | Person 4 Research, Results & Report Assembly |
| --- | --- | --- | --- |
| Key dependency: Hannah must share DTM and CHM outputs before Persons 2 & 3 can begin their analysis work. |  |  |  |

Timeline (April – May 2026)

| Date | Task | Who | ✓ |
| --- | --- | --- | --- |
| Week 1 Apr | Set up R environment: install lidR, terra, sf, RMCC, future packages. Configure parallel processing (2 cores). | Hannah |
| Week 1 Apr | Research scientific literature on LiDAR forest inventory methods (DTM, CHM, AGB, VCC). Begin Introduction draft. | Person 4 |
| Week 2 Apr | LiDAR processing: noise removal (SOR), ground classification (MCC), DTM generation (Kriging, 2m). Export DTM. | Hannah |
| Week 2 Apr | Draft Objectives section and Methodology outline (to be completed as processing finishes). | Person 4 |
| Week 3 Apr | Point cloud normalisation, CHM generation (pit-free algorithm, 1m). Post-process CHM (fill/smooth). Export outputs. | Hannah |
| Week 3 Apr | Finalise Methods section — processing pipeline complete. ✔ DONE | Hannah |
| Week 4 Apr | Area-Based Approach (ABA): extract LiDAR metrics per stand. Estimate AGB and VCC at stand/pixel level. | Person 2 |
| Week 4 Apr | Individual Tree Detection (ITD): apply tree segmentation algorithm. Extract per-crown metrics. | Person 3 |
| Week 1 May | Compare AGB/VCC estimates: pixel level vs crown level. Statistical summary. | Person 2 + 3 |
| Week 1 May | Produce graphical outputs: DTM, CHM, AGB map, VCC map, ITD crown map. | Person 3 |
| Week 2 May | Write Results section: present all maps and statistics. | All |
| Week 2 May | Write Discussion: interpret inventory estimates, compare methods, limitations. | All |
| 13 May | Assemble final PDF report. Check structure: ID, Intro, Methods, Results, Discussion, Sources. | All |
| 16 May | Final review. Attach R script. Compress to PDF + R script for submission. | All |
| 18 May ⚠️ | SUBMIT: PDF + R script to OneDrive (Course_UAV_LiDAR_ISA_2026) or Fenix. HARD DEADLINE. | All |

Hannah — LiDAR Processing & Methods Writing (Critical Path)  ✔ COMPLETE

Project Organisation & Setup ☑ Create shared OneDrive folder: Course_UAV_LiDAR_ISA_2026 / GroupNUMBER ☑ Set up subfolders: 01_Data, 02_Scripts, 03_Processing, 04_Outputs, 05_Report ☑ Share OneDrive folder with all group members and confirm access ☑ Share this to-do list with the group and assign names to Person 2, 3 & 4 roles ☑ Confirm LiDAR dataset assigned to your group and download to 01_Data folder ☑ Set up shared file naming convention for all outputs (e.g. GroupX_DTM_2m_KRI.tif) ☑ Send group message to confirm everyone has folder access and knows their tasks LiDAR Processing Pipeline ☑ Set up R environment with required packages (lidR, terra, sf, RMCC, future) and configure parallel processing ☑ Load raw LiDAR point cloud (.las/.laz) using readLAS and readLAScatalog; generate spatial index ☑ Visualise point cloud by RGB, intensity, and elevation; run las_check() for quality control ☑ Remove duplicate points and apply SOR noise filter (k=10, m=3); export cleaned point cloud ☑ Ground classification using MCC algorithm (scale=1.5, curvature=0.3) via tiled LAScatalog workflow ☑ MCC selected over PMF for superior performance in structurally complex eucalyptus stands ☑ Clip classified point cloud to stand boundaries using shapefile ☑ Generate DTM at 2m resolution using Kriging interpolation (k=40); mask to study area and export ☑ Kriging preferred over TIN/IDW for adaptive spatial modelling ☑ Normalise point cloud heights using TIN constrained to Kriging DTM; remove negative height points ☑ Generate CHM at 1m resolution using pit-free algorithm; apply NA-fill and smoothing; export all versions ☑ Share DTM and CHM outputs with rest of group — required before Persons 2 & 3 can proceed Methods Writing — Presentation2.pptx ✔ COMPLETE ☑ Methods section written and saved in Presentation2.pptx (04_documents folder) — DONE ☑ Justification of algorithm choices (MCC over PMF; Kriging over TIN/IDW) included — DONE ☑ Share Presentation2.pptx with group via OneDrive — DONE

Person 2 — ABA Analysis, Tree Detection & Introduction

Processing ☐ Receive normalised point cloud, DTM and CHM from Hannah ☐ Area-Based Approach (ABA): extract LiDAR height and density metrics per stand/pixel grid ☐ Metrics: mean height, max height, percentile heights (p25, p50, p75, p95), canopy cover density ☐ Apply allometric models or regression to estimate Aboveground Biomass (AGB) per pixel ☐ Apply volume equations to estimate Wood Volume with Cork (VCC) per pixel ☐ Summarise AGB and VCC estimates at stand level (aggregate per polygon) ☐ Export AGB and VCC rasters — share with Person 3 for crown-level comparison ☐ Copy final AGB and VCC .tif files to 05_outputs folder Writing ☐ Research and collect 2–3 scientific articles on LiDAR-based AGB/VCC estimation and ABA methods ☐ Draft Introduction section: context of LiDAR drone use in forest monitoring ☐ Draft Objectives section: summarise the 3 main deliverables from the assignment brief ☐ Write up ABA methodology steps and pass notes to Person 4 for report integration

Person 3 — Individual Tree Detection, Mapping & Results

Processing ☐ Receive CHM from Hannah and AGB/VCC rasters from Person 2 ☐ Apply Individual Tree Detection (ITD) algorithm to CHM (local maxima + watershed segmentation) ☐ Extract per-crown metrics: tree height, crown area, crown volume ☐ Apply allometric models to estimate AGB and VCC per individual tree crown ☐ Aggregate crown-level estimates to stand level; compare with ABA pixel-level outputs from Person 2 Cartographic Outputs (all with legend, scale bar, north arrow) ☐ AGB map (pixel level) ☐ VCC map (pixel level) ☐ Individual tree crown segmentation map ☐ Copy all final map .tif files and crown shapefile to 05_outputs folder Writing ☐ Research and collect 2–3 scientific articles on ITD methods and crown-level forest inventory ☐ Write Results section: present all maps and statistics (ABA and ITD outputs) ☐ Write up ITD methodology steps and pass notes to Person 4 for report integration

Person 4 — Comparison Analysis, Discussion & Report Assembly

Processing ☐ Receive AGB/VCC pixel-level rasters (Person 2) and crown-level estimates (Person 3) ☐ Produce statistical comparison of ABA vs ITD estimates for AGB and VCC ☐ Summary table: mean, SD, min, max at stand level for both methods ☐ Produce comparison figure or chart for inclusion in report Writing & Report Assembly ☐ Research and collect 1–2 articles on pixel vs crown-level comparison in forest inventory ☐ Write Discussion: interpret AGB/VCC estimates, compare ABA vs ITD approaches, note limitations ☐ Write Sources/References section — all data sources, R packages, and cited articles ☐ Extract Methods content from Presentation2.pptx (04_documents) and format for report — do not alter content ☐ Assemble final PDF report with correct structure: ☐ 1. Identification (title, group members, course, ISA, data sources) ☐ 2. Introduction & Objectives (from Person 2) ☐ 3. Methods — extract from Presentation2.pptx (04_documents), convert to report prose, no rewriting of content) ☐ 4. Graphical Presentation of Results (from Person 3) ☐ 5. Discussion ☐ 6. Sources ☐ Insert all cartographic outputs from Person 3 with captions ☐ Copy final PDF report and R script to 05_outputs folder ☐ Confirm 05_outputs contains all required files before zipping (see shared checklist) ☐ Proofread and format full report; attach Hannah's R script for submission

Shared Submission Checklist — Complete by 18 May 2026

Final deliverable checklist (tick off before submitting): - PDF report with all sections completed (ID, Intro, Methods, Results, Discussion, Sources) - R script (.R file) attached — Hannah's processing script - DTM raster (.tif, 2m resolution, Kriging) - CHM raster (.tif, 1m resolution, pit-free — base, filled, and smoothed versions) - AGB map (.tif, pixel level) - VCC map (.tif, pixel level) - Individual tree crown segmentation map included in report - AGB and VCC comparison table (pixel vs crown level) included in report - All cartographic outputs include legend, scale bar, and north arrow - Submitted to OneDrive (Course_UAV_LiDAR_ISA_2026) OR Fenix by 18 May 2026 Hard Deadline: 18 May 2026 ¦ Late submissions will not be accepted